title: Joint Cadence — Interlegal × Cyprus Partner Operating Rhythm

status: FINAL

language: english

controlling: true

prepared_by: Interlegal Senior + PM

finalised_by: Interlegal Partner

gate_required: []

audience: Interlegal staff + Cyprus partner staff (per ADR-006); covers all four Cyprus-side roles

created: 2026-05-17

# Joint Cadence — Interlegal × Cyprus Partner Operating Rhythm

Purpose: one shared operating cadence binds Interlegal department and Cyprus partner firm(s) into one joint production system. Without explicit cadence, joint workstreams (per ADR-006 ownership matrix + ADR-005 G0-G6 gates) drift — G5 sign-offs slip, evidence handoffs lose audit-trail, ADR interpretation diverges silently between firms.

Scope: every cadence event below is partner-agnostic — applies to any Cyprus partner constellation onboarded via Trek 05 (single-firm or split-firm). Partner-specific configuration (named individuals, calendar invitations, fee bands) lives in SOW + matter cockpit, not in this document.

## Cadence layer 1 — Weekly G4/G5 Calibration Call

When: every Tuesday, 14:00 Cyprus time / 13:00 Kyiv time. 45 minutes. Owner: Interlegal Senior chairs; Cyprus tax advisor mandatory; other Cyprus roles join when matter touches their gate. Format: matter-by-matter walkthrough + open-issues list + 1 ADR/tax-position discussion.

### Standing agenda

- Roll call (2 min) — confirm attendance per active matters

- Matter-by-matter G5 pipeline (≈ 25 min) — for each matter in stages 2.x – 5.x:

  - Current stage + gate status (G0/G1/G2/G3/G4/G5/G6)

  - Evidence pack handoff status (Interlegal → Cyprus)

  - Open G5 questions / blockers

  - Next handoff target date

- Open issues (≈ 10 min) — anything not matter-specific: ADR ambiguity, evidence-collection friction, SLA misses, partner economics flags

- One ADR / tax-position deep-dive (≈ 5 min) — rotating: each week one ADR or one Tax Assumptions Register row is re-read aloud + discussed for current-practice fit

- Action items (3 min) — captured + assigned + dated

### Outputs

- Action-items list pushed to matter cockpits same day

- Any ADR-drift flagged → entered in AMENDMENTS.md queue for partner review

- Any TAR row flagged → quarterly review batch

### When to skip / reschedule

- Cancel only if both Interlegal Senior + Cyprus tax advisor unavailable. Otherwise hold with replacement attendees.

- If <2 active matters in pipeline, shorten to 20 min status sync.

- Public holiday in CY or UA — reschedule to next available business day.

### Logged in matter cockpit

Each matter cockpit shows last weekly-cadence date + key handoff decisions. Engine appends a cadence_log entry on each call.

## Cadence layer 2 — Monthly Cross-Firm Calibration

When: last Wednesday of each month, 14:00 Cyprus time. 90 minutes. Owner: Interlegal Senior + Interlegal PM + all four Cyprus-side roles (audit / tax advisor / corporate services / legal). Format: retrospective on past-matter findings + ADR-interpretation alignment + Tax Assumptions Register working session.

### Standing agenda

- Past month — closed matters review (≈ 30 min)

  - 1-3 closed matters per month walked through

  - What worked / what slipped / where did joint-cadence catch (or miss) an issue?

  - Anonymise if client-sensitive — focus on process + decision quality

- ADR interpretation alignment (≈ 25 min)

  - Pre-circulated: 1 ADR section nominated by either side

  - Discussion: do both firms apply this the same way? Where does interpretation drift?

  - Output: either confirm alignment OR draft amendment to AMENDMENTS.md

- Tax Assumptions Register working session (≈ 20 min)

  - Cyprus tax advisor + ICPAC auditor rate Confidence on 5-10 TAR rows

  - Flag rows for quarterly review (downgrade Confidence, update Source, change Trigger)

- Open partner-economics / SOW issues (≈ 10 min)

  - Out-of-scope items / re-banding requests / SLA slippage trends

  - Escalate to quarterly retro if material

- Action items (5 min)

### Outputs

- Closed-matter learning notes appended to glossary/closed-matter-learnings.md (anonymised)

- ADR-drift items raised → either confirmed-aligned OR new amendment queued

- Updated TAR rows committed to glossary/tax-assumptions.md

- Open SOW items escalated to quarterly retro if not resolvable in-meeting

### When to skip

- Cancel if no closed matters in past month AND no ADR-drift flags AND no TAR rows due review. Otherwise hold.

## Cadence layer 3 — Quarterly Retrospective

When: last Friday of each quarter (Mar / Jun / Sep / Dec), 14:00 Cyprus time. 2 hours. Owner: Interlegal Partner + Cyprus senior partner; all Day-2 Trek-05 roles required; Interlegal Senior + PM present. Format: structured retrospective on what’s working, what’s not, partner economics, calibration test on a fresh anonymised matter scenario.

### Standing agenda

- Past quarter — metrics review (≈ 25 min)

  - Matters closed / in-flight / pre-G0

  - G3 → G4 SLA hit rate

  - G4 → G5 SLA hit rate

  - G5 sign-off turnaround average (target 5-10 working days standard; 48h urgent)

  - Ruling acceptance rate (if rulings closed in quarter)

  - Pre-export validator block rate (Sprint 1.6 metric)

- Working / not working (≈ 30 min)

  - Each role contributes 2 things working + 2 things not

  - Group into themes; assign owner for top 3 friction items

- Partner economics review (≈ 25 min)

  - Fee bands per matter band — are they tracking actual scope?

  - Out-of-scope creep — should any item move to base S2/S3?

  - Cyprus partner success-fee tracking (banking intros, ruling success)

  - Re-band proposals → quarterly close, signed amendment to SOW if approved

- Calibration test (≈ 30 min)

  - Pre-circulated anonymised matter scenario

  - Each role gives G5 verdict + reasoning

  - Compare answers across firms + within firms

  - Output: calibration confidence + any flag for additional training

- Next quarter priorities (≈ 10 min)

  - Carry-over actions

  - New focus items (e.g. evidence-pack streamlining, new memo type, change in Cyprus Tax Dept practice)

### Outputs

- Quarterly metrics snapshot → committed to glossary/partner-quarterly-metrics.md

- Working/not-working themes → top 3 with owners + deadlines

- Partner economics re-band proposals → SOW amendment(s) drafted within 30 days

- Calibration drift findings → either confirmed-aligned OR additional training scheduled

### When to skip

- Never skip. If neither senior partner can attend, postpone within same month; do not skip the quarter.

## Cadence layer 4 — Annual Partner Economics Review

When: January (typically week 2-3, after both firms’ year-end financial close). Owner: Interlegal Partner + Cyprus senior partner; full senior leadership both sides. Format: Annual review of partner relationship + fee structure + ADR-006 row-by-row + renewal decision.

### Standing agenda

- Annual outcomes — matter volume, fee revenue, margin (per firm)

- ADR-006 row-by-row — for each ownership-matrix row, is it still accurate? Has reality drifted?

- Fee band review — are S0/S1/S2/S2+/S3 fee bands still accurate? Cyprus partner fees still in band? Pass-through items still pass-through?

- Exclusivity terms — bidirectional opt-in renewal (first 18 months default; renewal vote in year 2)

- Renewal vote — either party may signal renewal / re-negotiation / wind-down; off-boarding clause 90-day notice per ADR-006

- Backup partner status — second ICPAC firm warm-relationship maintenance review

### Outputs

- Annual review minute → both firms sign + file

- Any structural change → AMENDMENTS.md entry (e.g. partner change, fee structure change)

- Renewal / wind-down decision recorded

## Special cadences (event-triggered)

### Urgent G5 escalation

Trigger: matter requires G5 sign-off in < 48h (regulatory deadline; client commercial deadline). Process: Interlegal PM signals Cyprus tax advisor + ICPAC auditor + Bar member via dedicated escalation channel; 4h response window; 24h sign-off SLA. Tracked in matter cockpit as urgent flag.

### G6 second-review coordination

Trigger: matter hits one of 9 G6 triggers (per ADR-005); external counsel engagement needed. Process: Interlegal partner + Cyprus tax advisor jointly nominate external counsel from preferred-network list (Cyprus / Athens / London tax counsel). Coordination call within 5 working days; G6 turnaround 10-20 working days standard.

### ADR amendment process

Trigger: monthly cadence or quarterly retro identifies ADR-drift requiring formal amendment. Process: Interlegal Senior drafts amendment (per PROJECT_METHODOLOGY.md discipline); circulated to both firms; signed within 30 days; appended to AMENDMENTS.md.

### Backup-partner activation

Trigger: primary Cyprus partner unable to deliver (capacity / conflict / SLA persistent slippage / off-boarding). Process: per ADR-006 risk section — second ICPAC firm activated; 90-day handover protocol; matters reassigned; Trek 05 onboarding for new partner staff.

## Cadence calendar overview

| Cadence | Frequency | Duration | Mandatory roles |
| --- | --- | --- | --- |
| Weekly G4/G5 calibration | Every Tue 14:00 CY | 45 min | Interlegal Senior + Cyprus tax advisor |
| Monthly cross-firm calibration | Last Wed of month | 90 min | All Day-2 Trek-05 roles |
| Quarterly retrospective | Last Fri of quarter | 2 hr | All roles + Interlegal partner + Cyprus senior partner |
| Annual partner economics review | January | half-day | Senior leadership both sides |
| Urgent G5 escalation | Event-triggered | 4h response, 24h sign-off | Per ADR-006 |
| G6 second-review coordination | Event-triggered | 5 days kickoff | Interlegal partner + Cyprus tax advisor + external counsel |
| ADR amendment process | As needed | 30 days sign-off cycle | Interlegal Senior drafts; both firms sign |
| Backup-partner activation | Crisis | 90 days handover | Per ADR-006 risk section |

## Why a written cadence

Three failures occur silently if cadence is not written:

- G5 slippage cascade — without weekly calibration, G5 issues are first surfaced on G5 sign-off day. Late-stage discovery + no time to remediate. Weekly cadence catches issues at G3/G4 evidence-pack stage.

- ADR drift between firms — each firm reads ADR slightly differently. Without monthly cross-firm alignment, divergence is invisible until a matter blows up. Monthly cadence surfaces drift + triggers amendment.

- Partner-economics resentment — without quarterly review, scope creep accumulates silently. Cyprus partner overdelivers without re-band; eventually quality drops or relationship breaks. Quarterly retro + annual review keep economics calibrated.

Cadence is the operating system. Without it, the technical operating system (engine + portal + ADRs) cannot function as a joint production system.

Related: [[decisions-005-process-gates]] (G0-G6 model), [[decisions-006-cyprus-contractor-strategy]] (ownership matrix), [[decisions-008-tax-assumptions-register]] (TAR working sessions), [[learn-cyprus-contractor]] (Trek 05 onboarding), [[AMENDMENTS]] (amendment discipline), process/stages.md (6×14 stage map).